## Sheet1
Week
Person | Task | Start | End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Benjamin | Follow tutorials | 1 | 3 | bar: Week 1 to Week 3
Callum |  | 1 | 3 | bar: Week 1 to Week 3
Chris |  | 1 | 3 | bar: Week 1 to Week 3
Benjamin | Create Auxentius Bithnus' home | 4 | 5 | bar: Week 4 to Week 5
Callum |  | 4 | 6 | bar: Week 4 to Week 6
Chris |  | 4 | 5 | bar: Week 4 to Week 5
Benjamin | Create quest story line | - | -
Callum |  | - | -
Chris |  | 6 | 6 | bar: Week 6
Benjamin | Create quest dialogue | - | -
Callum |  | - | -
Chris |  | 7 | 7 | bar: Week 7
Benjamin | Create Dwemer dungeon | 6 | 6 | bar: Week 6
Callum |  | 7 | 7 | bar: Week 7
Chris |  | 8 | 8 | bar: Week 8
Benjamin | Implement written quest | 7 | 8 | bar: Week 7 to Week 8
Callum |  | - | -
Chris |  | - | -